## Sheet1
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description
6oOAfGFAqUSFt8o-VBNwQZcAJrBF | UX/UI: Findings Update | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
BmEPNz0Xl0yKBRJnQ7KaAJcAEgQT | Software Deployment | TET - Travel Exp Tool | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 07/07/2025 | FALSE | TRUE |  |  |  |  | TET
Cba93iFyGUOGJ7lzi_oGLZcALJJg | App Production Planning Tool | App Production Planning | In progress | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/19/2025 | 03/26/2025 | 09/30/2025 | FALSE | FALSE |  |  |  |  | ProdPlanning
GTK5_yr_FkqglhIqx4bRt5cADsY_ | UX: Admins Database Creations | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
I7V1bQKWTkal_xV7Z5PrlJcAGLQ7 | UX/UI: Review (if necessary) | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
WmWQXN1KmEWJy8U_d3VifZcACrSY | App REWO - CGMS Data Extraction - Varianta Dorita | App REWO TB | Not started | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  |  | FALSE | FALSE |  |  |  |  | REWO
_gIyA4Q3u02QMB2oHwp2bpcAKIMB | UX: Windows & Active Directory Auth | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
g2XEwqg3Y0CPx4FExHqbfJcAGziR | UX: Report Generation + E-Mail | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
jAumijUbkkCo884VkrYJRZcAGk7R | Production Planning Tool - Error Handling, User Feedback, Testing and Bug Fixes | App Production Planning | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE |  |  |  |  | ProdPlanning | - Add error dialogs and status messages for all critical operations. - Log errors and important events. - Test all features after each major change. - Fix import issues for both direct script and package execution. - Ensure compatibility across different run modes.
o_YKSHifq0Sp1pC-Itiem5cAJW_B | InfoKiosk Availability Check | InfoKiosk | Not started | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/27/2025 |  | 07/04/2025 | TRUE | TRUE | [5 empty] | Maintanence check - various Infopoints
qQjS-7WjLkeKEXD3fED1sZcAIKsi | UX/UI : Function for starting a new Audit | AuditApp | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE
tV-fjVx790OBSKUuEJfjSJcAELeY | Production Planning Tool - Setari Tab: User Settings | App Production Planning | In progress | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE |  |  |  |  | ProdPlanning | - Add theme toggle (light/dark) that updates all widgets. - Add settings for calendar year, font size, and notifications. - Allow users to apply and persist their preferences.
is4NxToOJkir8Ldbhsg_v5cAMiiP | TET Knowledge Transfer | TET - Travel Exp Tool | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 07/10/2025 | FALSE | FALSE | 07/24/2025 | Boboc, Alexandru-Florin
fMmjYP18Q0KmT5t2dCxbLZcAJOkr | Installation of v2.61 of TET | TET - Travel Exp Tool | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 07/10/2025 | FALSE | FALSE | 07/24/2025 | Boboc, Alexandru-Florin |  |  | TET
E5Ca83hfXE-sL-qiZ7qlWZcAILuV | UI/UX: Audit Close | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
Q2hFnGtC7EKwVNpD52K9JZcAMRsF | UI/UX: Dashboard Modernization | Scope | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 07/01/2025 | 07/01/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
13mej32JhU-KWSTTMUeVEpcAL0wN | UX: Users Database Creations | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
y4ZYy3jPLUuS8IbOH6bOrpcAJp5- | UX/UI : Area Categorization ( Subarea, Machine ) | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
VYMJ8QysbEK_Va65pTkCxJcADVdn | UX/UI : Participants Selection | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
XxKqeJA4d0qZ_pZG01kJKJcAIY6D | UX/UI: Auditors Selection | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 07/21/2025 | Boboc, Alexandru-Florin
FqPHnisVSkC-edaDSNDa_pcAE4lW | UX: Findings Database Creation | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 06/30/2025 | Boboc, Alexandru-Florin
KA7fNJM0r0ypII6g6UKG9ZcAJPUd | UI/UX: Findings Addition | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 06/30/2025 | Boboc, Alexandru-Florin
JPIy_NxLrkqE5iPUAwXcW5cAEJDF | UX/UI: Filtering by Status, Responsible and Area | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 06/30/2025 | Boboc, Alexandru-Florin
sxVlpJ5vbkWR-cy7RCzaEZcANS8h | UX/UI: Dashboard Creation | AuditApp | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/30/2025 | 06/30/2025 |  | FALSE | FALSE | 06/30/2025 | Boboc, Alexandru-Florin
S_aKYLGaYkyjrq9Z1LW0lJcAJT_I | InfoKiosk Availability Check | InfoKiosk | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/16/2025 |  | 06/27/2025 | FALSE | FALSE | 06/27/2025 | Boboc, Alexandru-Florin |  |  |  | Maintanence check - various Infopoints
Ya_h8e5uK0ShGWs-Tz0_gJcAHLSD | InfoKiosk Availability Check | InfoKiosk | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/13/2025 |  | 06/20/2025 | FALSE | FALSE | 06/16/2025 | Boboc, Alexandru-Florin |  |  |  | Maintanence check - various Infopoints
5Q9fjec09kmXU5njVxDpnJcAFPoM | InfoKiosk Availability Check | InfoKiosk | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/13/2025 |  | 06/13/2025 | FALSE | FALSE | 06/13/2025 | Boboc, Alexandru-Florin
CvAR7ly0zkG5k7jCC7lKm5cADZfx | Production Planning Tool - Design and Implement Main Application UI | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/13/2025 | Boboc, Alexandru-Florin | 2/2 | Apply a consistent, modern style across all widgets.;Build a main window with a tabbed interface (QF, Activitati zilnice, Setari, Dashboard). | ProdPlanning | - Build a main window with a tabbed interface (QF, Activitati zilnice, Setari, Dashboard). - Apply a consistent, modern style across all widgets.
bhcnZMyTyU6TSb20_7RKu5cAOYAI | App REWO - Scanare, Motiv and Bucati Security Restrections - Varianta Rapida | App REWO TB | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  |  | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin
SLUjIbiHYEOL_EFT7-oatJcAFjIz | App REWO - Inchidere/Alta Colectare Fixes - Varianta Rapida | App REWO TB | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  |  | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin
WjNOrfZatUyt3jHzMfbsc5cALvvZ | App REWO - Reasons Update - Varianta Rapida | App REWO TB | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  |  | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin
nCfOGLTOkUK7nWwMqquNVZcAB4fh | App REWO - User TB - Varianta Rapida | App REWO TB | Completed | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/19/2025 |  | 06/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | REWO
heoqf3tKnUWa9cOZ_9Y_MJcAOlyc | Production Planning Tool - Database Integration | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Use SQLite for persistent storage of all activities. - Create and manage tables for IT and MTE activities.
NTiu4QKZAECacnaw-QtQ3ZcAMo9P | Production Planning Tool - Excel Import/Export | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Implement Excel import for IT&MTE activities. - Ensure imported data is correctly parsed and inserted into the database.
2gCdRrvbZ0-EcKJEKSSStpcAAUoD | Production Planning Tool - Dashboard Tab: Activity Summary | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Show a summary of all activities, productivity, and recent changes. - Display statistics (counts, workdays, completed activities). - Optionally, visualize data (e.g., pie chart if matplotlib is available).
lKnv2sKVh0ScPEw1KugxppcAEqWd | Production Tool Planning - Activitati Zilnice Tab: Unified Activities Table | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Merge IT and MTE activities into a single table. - Display all relevant columns for both types. - Support editing of activities.
F_nik5-ReUe22nt4HUXO0pcAFF70 | Production Planning Tool - QF Tab: Calendar View by Quarters | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Implement a calendar view divided by yearly quarters. - Display all activities (IT and MTE) for each day, with details. - Support multiple activities per day.
-SSn7ArdMEmO-eMeQH2Q4ZcACnu1 | Production Planning Tool - Session Management | App Production Planning | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/06/2025 |  | 09/30/2025 | FALSE | FALSE | 06/06/2025 | Boboc, Alexandru-Florin |  |  | ProdPlanning | - Implement session timeout and auto-logout for security. - Reset session timer on user activity.
uH_F0VR6m0i3xqiuVZDn35cAEz2w | REWO Cards Update | Scope | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 06/02/2025 |  | 06/06/2025 | FALSE | FALSE | 06/02/2025 | Boboc, Alexandru-Florin
ebOCdzkbZUaawMnfzYea6pcAKmY- | TET - local configurations | TET - Travel Exp Tool | Completed | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/19/2025 | 05/15/2025 | 06/30/2025 | FALSE | FALSE | 05/30/2025 | Boboc, Alexandru-Florin |  |  | TET
jgR3kUEARkme_Z9TV7W4fZcAGwSP | Change in REWO app - add a new Reason | Scope | Completed | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/30/2025 |  | 06/06/2025 | FALSE | FALSE | 05/30/2025 | Boboc, Alexandru-Florin |  |  | REWO | Virlan, Claudia in Chat with Alexandru-Florin at May 29 2025, 12:37 PM: https://teams.microsoft.com/l/message/19:59eab854-7df5-4733-8587-5a245cf6912d_8eb099d5-26a6-4e73-81d5-3395fd89615f@unq.gbl.spaces/1748511444473?context=%7B%22contextType%22:%22chat%22%7D
JL1dSGfgPkiE5RhZUY8MA5cANpUV | FleetM Automatization App for Monthly Cost | Fleet Management - app Infochiosc | Completed | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/19/2025 | 05/19/2025 | 05/30/2025 | FALSE | FALSE | 05/21/2025 | Boboc, Alexandru-Florin | 0/1 | De trimis requestul - Claudia V | FleetM
aUhXr4j_k0mhkvh5wft9MJcAJ0vn | Change Tool - modificari | Scope | Completed | Medium | Boboc, Alexandru-Florin | Virlan, Claudia | 05/19/2025 | 05/12/2025 | 05/23/2025 | FALSE | FALSE | 05/19/2025 | Boboc, Alexandru-Florin | 2/2 | De trimis link si o mica documentatie - Alex B;De curatat variantele intermediare - Alex B | Existing app | http://10.202.80.13/ChangeTool/ - Link Aplicatie Finala
QaCTjZH130-zKKqMbr01bJcAH-_2 | Verificare VS appPublish in the same URL/name | App REWO TB | Completed | Medium | Donat, Cristian-Claudiu;Virlan, Claudia;Boboc, Alexandru-Florin | Virlan, Claudia | 05/05/2025 | 05/05/2025 | 05/09/2025 | FALSE | FALSE | 05/19/2025 | Virlan, Claudia |  |  |  | Da, se poate. 1. Se da Publish la app intr-un folder cu acelasi nume ca cel anterior. 2. Se redenumeste folderul vechi din wwwroot/Inetpub 3. Se muta noul folder cu Published App pe serverul app in wwwroot/Inetpub 4. Din IIS se transforma in App
0WWxuWfCG0evWagvYJRWkJcAKvDm | Ozeki Restruct | Scope | Completed | Low | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 |  |  | FALSE | FALSE | 03/20/2025 | Boboc, Alexandru-Florin |  |  | UnplannedM
HfF7MoM5mEOpNy9x4hP5zpcAOZxd | Restruct ChangeTool (GO/NOGO Process) | TET - Travel Exp Tool | Completed | Important | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 02/10/2025 | 02/20/2025 | FALSE | FALSE | 03/20/2025 | Boboc, Alexandru-Florin |  |  | High
LgeVkEzXck6kEgacp--FppcABDnL | Rework pagina Derogare (ChangeTool) | Scope | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 02/10/2025 | 02/20/2025 | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
miEhRgPu_0qWoKvxCu-qGZcAJPtb | LANDesk Automation | Migrare CTOO - IE | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 01/27/2025 |  | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
sThK22hoqECkQVpYLqiB7JcAEOw6 | Password/ConnectionString Finder | Migrare CTOO - IE | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 12/06/2024 |  | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
Sk_pV2Q9_UaQosMkm4YOjZcAKLm5 | Zabbix Hosts check Automation | Migrare CTOO - IE | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 01/23/2025 |  | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
-yxBh3En_02xKuGWcQ-OoJcAL67y | Restruct Timinet | Migrare CTOO - IE | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 02/22/2025 |  | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
nJBb7wPCckuJZNyEoIWMrJcAMk-3 | Automatizare Fleet Management | Migrare CTOO - IE | Completed | Medium | Boboc, Alexandru-Florin | Boboc, Alexandru-Florin | 02/13/2025 | 10/21/2024 |  | FALSE | FALSE | 02/13/2025 | Boboc, Alexandru-Florin
cGnQRKhT4ECm5KpLn9S9HZcAMfBl | (WO DataCollection) Deliver Pilot User+Admin Interface | TET - Travel Exp Tool | Completed | Medium | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 11/01/2024 | 11/08/2024 | FALSE | FALSE | 02/13/2025 | Virlan, Claudia
yzO9-GCWiUmv-73RgxNnJ5cAJeGd | (WO DataCollection) Inside Admin Interface Testing | App REWO TB | Completed | Medium | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 10/21/2024 | 10/25/2024 | FALSE | FALSE | 11/01/2024 | Donat, Cristian-Claudiu
A-WPydX_BUivqVnM779L05cAMtFF | (WO DataCollection) Dev. Admin Interface | Migrare CTOO - IE | Completed | Medium | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 10/07/2024 | 10/25/2024 | FALSE | FALSE | 10/09/2024 | Boboc, Alexandru-Florin
68tJdbhjkUql3FtmTMiJqpcADl-U | (WO DataCollection) Inside Testing | App REWO TB | Completed | Medium | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 09/30/2024 | 10/04/2024 | FALSE | FALSE | 10/01/2024 | Donat, Cristian-Claudiu
tCHrzpS16EqX9-u85-BYyZcANiS6 | (WO DataCollection )Dev. User Main Page | Migrare CTOO - IE | Completed | Medium | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 09/30/2024 | 09/30/2024 | FALSE | FALSE | 09/24/2024 | Donat, Cristian-Claudiu
_02MCYHQ3U2kJC9MZtcI75cANBBd | (WO DataCollection) Dev. User Login | Migrare CTOO - IE | Completed | Low | Donat, Cristian-Claudiu;Boboc, Alexandru-Florin | Donat, Cristian-Claudiu | 09/11/2024 | 09/09/2024 | 09/18/2024 | FALSE | FALSE | 09/17/2024 | Donat, Cristian-Claudiu
vijN8sKK1UWerRanwHiqgZcAOoLi | Automate Empty Carrier by excel export | Warehouse - Tiretracking | In progress | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/24/2025 | 07/24/2025 |  | FALSE | FALSE |  |  |  |  | WareHouse
vllXHc_79UKNLteKWsqQx5cABZ-3 | RMEA TPX Machines (NO DATA past 26.06.2025) | PowerBI stuff | In progress | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 | 07/23/2025 |  | FALSE | FALSE |  |  |  |  | DB
wjb0UEzmfUiw_aB-3vNCIJcAJnl2 | Validare date Sidewall | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
3PAcGnIXxEKlcgZ600NQtJcACnZQ | Validare date Innerliner | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
WWKN1RhrEEipJgY-3LCkPJcABHVA | Creare pagina noua in PBI rep - Sidewall | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
D4CwQ3VCBE-CKFVPftQkjpcACUHC | Creare pagina noua in PBI rep - Innerliner | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
3qlgUGmCgUy0C2YI5IWISZcAMUtQ | Creare structura date Sidewall | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
G8YLwgXD8UqcgPzOq2DUrZcAAYpE | Creare structura SQL Innerliner | Evolution of IPOC, Dies, Compounds | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 06/06/2025 |  |  | FALSE | FALSE
2ItN1NTi1EuogltXcZRLIpcANYJE | New Gateways and Storage for PowerBI reports | Scope | Not started | Medium | Virlan, Claudia | Virlan, Claudia | 05/30/2025 | 06/02/2025 | 09/30/2025 | FALSE | FALSE |  |  |  |  | PowerBI | Macek Lukas: I would like to see Jochen Hebe involved in that, he is Global Team Lead for Manufacturing Analytics
Kr8ugxAXGEOIo0rVit--dJcAN0UH | Rework and Workoff report | PowerBI stuff | Not started | Medium | Virlan, Claudia | Vulpes, Mihaela | 05/28/2025 |  | 06/30/2025 | FALSE | TRUE | [5 empty] | SO OUT WITH : Paletizare, Weight Consumed (measure) , and (STOCK RW & STOCK WO (empty charts), Categorie transpose Total transpose
S9IljOTwz0-ROBLDXh2jtpcAEVPy | New Gateways, report publishing conditions | Scope | Not started | Medium |  | Virlan, Claudia | 05/27/2025 | 06/02/2025 | 06/06/2025 | FALSE | TRUE |  |  |  |  | PowerBI
k9f0zVtUX0qO0PZ8b36BJpcAHl18 | Improve DB Perf - rewrite/replace views | Scope | Not started | Medium | Vulpes, Mihaela;Virlan, Claudia | Vulpes, Mihaela | 05/23/2025 | 05/12/2025 | 12/31/2025 | FALSE | FALSE |  |  |  |  | DB
BO2MQ5DH2EeJ04Q1DbQZ9JcAKT99 | REwork Workof - consumption grafice | Scope | Not started | Medium | Virlan, Claudia | Virlan, Claudia | 05/19/2025 |  | 09/30/2025 | FALSE | FALSE |  |  |  |  | Existing app
Wicp4ZpffEScoKn5A_05i5cALRtk | MissingMaterial Compound - initial dataset | Scope | Not started | Medium | Virlan, Claudia | Virlan, Claudia | 05/19/2025 |  | 10/31/2025 | FALSE | FALSE |  |  |  |  | New dataset
cKatNk4NtkKqK05yMsTxPZcALKzH | CGMS DB02 Improvment - analyses | Scope | Not started | Medium | Vulpes, Mihaela | Virlan, Claudia | 05/14/2025 |  |  | FALSE | FALSE |  |  |  |  | DB
J_1cFE5PVUuppiuAUQY1ZZcAKl1j | CTOO - actualizare interfata raport - denumiri in Engleza | Migrare CTOO - IE | Not started | Medium | Zahamaicu, Victor | Virlan, Claudia | 05/08/2025 |  |  | FALSE | FALSE |  |  |  |  | CTOO
xj5b3m1wlk-PkCMoQLWrEZcACa5_ | CTOO - actualizare date in .pbix cu fisierul Excel trimis de Alis | Migrare CTOO - IE | Not started | Medium | Zahamaicu, Victor | Virlan, Claudia | 05/08/2025 |  |  | FALSE | FALSE |  |  |  |  | CTOO | In Transform Data, dupa ce schimbam sursa fisierului Excel cu ce primim de la Alis, mai trebui sa actualizam un JOIN in tabela data v3
2Jc26yNdn0GKfwqudvhR25cALeqa | Lista de view-uri si Proceduri stocate Tias067A | No Bucket | Not started | Medium | Virlan, Claudia | Virlan, Claudia | 04/03/2025 |  |  | FALSE | FALSE |  |  |  |  | DB
O60xv5ImbUm7mpz52R5tz5cAMrMS | Dezactivare Scheduled Refresh - rapoarte PBI inactive in ultimele 4 luni | PowerBI stuff | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Virlan, Claudia | 05/08/2025 | 05/08/2025 | 05/30/2025 | FALSE | FALSE | 07/24/2025 | Virlan, Claudia |  |  | PowerBI
13KgPaDKcUa4zYiiWgdCkpcAJ6sB | Ananliza posib aducere date live pt TB din CGMS | App REWO TB | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/21/2025 | 05/22/2025 | 05/30/2025 | FALSE | FALSE | 07/24/2025 | Virlan, Claudia |  |  | REWO | Complexitate mare ce duce la timp de refresh mare (sunt date de adus pentru toate cele 46 de masini, oar pentru fiecare in parte pentru fiecare subcomponenta). Nu se justifica consumul de resurse (dezvoltare DB si flux de date prin retea intre Client - server app - baza de date si inapoi).
rmbRlf8560CgnEKWCniifZcAKL0L | Confimare Florin Chuiselita | Fleet Management - app Infochiosc | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 06/06/2025 |  | 06/13/2025 | FALSE | FALSE | 07/24/2025 | Virlan, Claudia
STSiCWLZIkqOEom-maSpt5cAA2fT | Update Volume TB/CU for Led Panels May 2025 | Scope | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/30/2025 | 05/30/2025 | 05/30/2025 | FALSE | FALSE | 07/24/2025 | Virlan, Claudia |  |  | DB
7DuXD9JLyUGATIEIEY4WQ5cAP5dD | Acces Mustang | Scope | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/30/2025 | 06/02/2025 | 06/06/2025 | FALSE | FALSE | 07/24/2025 | Virlan, Claudia |  |  | PowerBI
JjIEVJt79k6ZNjdSeCLpw5cAAPRo | WOData app UPDATE | REWO Data Collection PBI report | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  | 07/17/2025 | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu | 3/3 | Change the update from 5 to 7 Minutes;HOST THE APPLICATION AT 7:00 for 1st shift;New Rejection Motive | WOData
k8s4wNfcgEOTYcJ2dwD2wJcAC2Y4 | Modify TireSearch app to include ColorCode | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
LH0R9TIRkEKxmDI_jQkIhJcALC5Q | Automatize TireRegister interface | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
4zHQ66Hd3Eabf3hbAHleZZcAMq4s | Metoda de stergere a Anvelopelor inregistrate in aplicatie dupa livrare | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 05/22/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
vGOC0CdE80uF5f6rCIDe5ZcAORLB | Update the WarehouseTireTracking apps | Warehouse - Tiretracking | Completed | Important | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu | 4/4 | Update TireDelete;Update TireSearch;Update EmptyCarrier;Update TireRegister | WareHouse
v3Tzayu4Tkazy6yliOOVDpcANKrt | Set Colorcode for WarehouseTireTracking | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu | 5/5 | Make a job that deletes excess data ;Make a procedure that gathers the data from the last day;Make a job that keeps the SQL up to date;Optimize the stored procedures;Grab Tire Object Data from MCAT | WareHouse
Zyiv2QhKgU-2HKa2Z2PpGpcALH6Q | Set KSP Capacity for WarehouseTireTracking | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 07/23/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
ipea30J-fUiD3wEMK-HDH5cAFq2X | (WarehouseTiretracking)TireRegister APP | Warehouse - Tiretracking | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/16/2025 |  |  | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | WareHouse | Look for a solution to lock a specific number of Tires/KSP by Tire type (Description)
EJP4dnFk1UaWfQp9cMCC_ZcAKLpw | FLEETM Pilot and Deployment for Testing on Infopoints | Fleet Management - app Infochiosc | Completed | Medium | Donat, Cristian-Claudiu;Virlan, Claudia | Donat, Cristian-Claudiu | 05/15/2025 |  | 06/13/2025 | FALSE | FALSE | 07/23/2025 | Donat, Cristian-Claudiu |  |  | FleetM
0ap4TJ2JNUm3V98tZlso5pcAEaRJ | verificare folosire user SA in rapoarte | Scope | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/27/2025 | 05/27/2025 | 06/05/2025 | FALSE | FALSE | 07/03/2025 | Virlan, Claudia |  |  | DB
FUfKL8T_eEaF9pPbxFEjrpcAD_ld | Data Optimization and Obsolete reports | Scope | Completed | Important | Vulpes, Mihaela;Virlan, Claudia | Vulpes, Mihaela | 06/23/2025 |  | 07/15/2025 | FALSE | FALSE | 07/03/2025 | Virlan, Claudia |  |  |  | Ceau, Am de transmis câteva chestii Nu știu daca ai fost anunțată si tu, dar am zis sa trimit si asta. Mi-sa dat task sa reducem din date , in principiu nu avem voie sa folosim import mode pentru modele care stocheze mai mult de 25 de luni de date, m-am uitat si am identificat 53, cred ca exista si mai multe.
ZSDmqPozj0G0bauDR6kJgpcAL9Fc | ReworkTB | Scope | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Vulpes, Mihaela | 06/26/2025 | 06/26/2025 | 06/26/2025 | FALSE | FALSE | 06/26/2025 | Vulpes, Mihaela | 4/4 | ShiftNumber;Power BI first dashboard ( pareto buc/module; buc/motive; buc/shiftcolor; chart : total pe articole;ShiftColor;ShiftDate |  | we cannot bring CGMS CapCompond for [ETL_DB].[dbo].[ReworkTB]
tJsOojqvikeqChuCvM-cf5cAIrXf | CGMS Apps user for SQL Services Rep Server | Improve DB Performance - rewrite / replace views | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 06/23/2025 | 06/23/2025 | 06/24/2025 | FALSE | FALSE | 06/26/2025 | Virlan, Claudia
KuCWMEnjkE6BkYUqLf7RcpcAIQTI | verificare job & modificare view | Scope | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Vulpes, Mihaela | 05/27/2025 |  | 05/28/2025 | FALSE | FALSE | 05/28/2025 | Vulpes, Mihaela |  |  | UnplannedM
M0zWXeXWv0ih6OjrCUa8wZcALfyj | optimizare unplanned maintenance - tabela +job in loc de view | PowerBI stuff | Completed | Medium | Vulpes, Mihaela | Vulpes, Mihaela | 05/08/2025 | 05/08/2025 | 06/30/2025 | FALSE | FALSE | 05/28/2025 | Vulpes, Mihaela | 3/3 | create table [tbl_UnplannedMaintenance_new];procedura stocata ;job | UnplannedM
c644j7TqIUOmil1h-gb98JcAHP9u | Untitled task | Scope | Completed | Medium |  | Virlan, Claudia | 05/27/2025 | 06/02/2025 | 06/06/2025 | FALSE | FALSE | 05/27/2025 | Virlan, Claudia
6Rn1BFti2EOeit7KhQYHSJcAGXI- | Validare coduri Unplanned Maintenance | PowerBI stuff | Completed | Important | Vulpes, Mihaela | Vulpes, Mihaela | 05/08/2025 | 05/07/2025 | 06/30/2025 | FALSE | FALSE | 05/26/2025 | Vulpes, Mihaela | 1/1 | lista CGMS codes | UnplannedM | Department Responsible: - IT - MTE - Process - Prod Unplanned Maintenance (only MTE responsible)
OwyqxFFy30-QUA2yZJl3O5cAGKmv | Improve DB Perf - with (nolock) vw&sp | Scope | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Virlan, Claudia | 05/19/2025 |  | 05/23/2025 | FALSE | FALSE | 05/23/2025 | Vulpes, Mihaela | 2/2 | TIAS067A;TIAS101A | DB | server [TITM09S03MS03\TIT_I3].[ctReports]- reporting server SFI , vechi, for historical data only
3X73G0upSEe_7vW3R4jM7ZcAGE4z | Improve CGMS DB - with (NOLOCK) - TIAS101A storedprocedure | Scope | Completed | Medium | Vulpes, Mihaela | Vulpes, Mihaela | 05/22/2025 |  | 05/23/2025 | FALSE | FALSE | 05/23/2025 | Vulpes, Mihaela |  |  |  | Database: [ETL_DB] 1.[dbo].[GT_Rework_GET_Order] 2.[dbo].[LHPerformance_EXT_volum] 3.[dbo].[LHPerformance_TB_AreaRecordDay] 4.[dbo].[LHPerformance_TB_AreaRecordShift] 5.[dbo].[LHPerformance_TB_OperatorRecord] 6.[dbo].[LHPerformanceBottomPannel_Step1] 7.[dbo].[LHPerformanceBottomPannel_Step2] 8.[dbo].[LHPerformanceMiddlePannel] 9.[dbo].[LHPerformanceOI] 10.[dbo].[LHPerformanceScrap]
QJNSzsDK5kuFF37a-iKeW5cAO6Zk | Improve DB performance - add with (NoLock) | Scope | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/15/2025 |  |  | FALSE | FALSE | 05/23/2025 | Virlan, Claudia | 0/1 | Creare lista view-uri | DB
F2kdSGO9zUC5PFnYmu3J6ZcAGNLb | Creare tabela FleetCost pentru transfer date din Fleet Import - PBI source | No Bucket | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/21/2025 | 05/22/2025 | 05/23/2025 | FALSE | FALSE | 05/23/2025 | Virlan, Claudia |  |  | FleetM
GPDExW5nF0K3tGeMa7MwbZcAGr9H | Improve CGMS DB - with (NOLOCK) - TIAS067A storedprocedure | Scope | Completed | Medium | Vulpes, Mihaela | Vulpes, Mihaela | 05/22/2025 |  | 05/23/2025 | FALSE | FALSE | 05/22/2025 | Vulpes, Mihaela | 2/2 | NewERT;BD_Timisoara |  | Database: [BD_Timisoara] StoredProcedure: 1.[dbo].[AIS_Auto_GETRecentAction] 2.[dbo].[AIS_Event_Count_STG_to_FINAL] 3.[dbo].[Update_CGMS_TEEP] Database: [NewERT] StoredProcedure: 1.[dbo].[Update_GreenTire_Quantity] 2.[dbo].[usp_CGMS_ERT_DailyLosses] ( 3.[dbo].[usp_CGMS_ERT_DailyProd] - > FROM [TITM09CGMDB01].[CGMS].[dbo]....changed it but still "Msg 18456, Level 14, State 1, Line 10 Login failed for user 'tableau_user'." 4.[dbo].[usp_CGMS_ERT_DailyProd_backup] same )
AXKLl0r_K0yomDl0I5rk3ZcAMz53 | Import Date in SQL for WarehouseTireTracking | Fleet Management - app Infochiosc | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/29/2025 |  |  | FALSE | FALSE | 05/22/2025 | Donat, Cristian-Claudiu |  |  | WareHouse | 2nd step from Number of Tires/KSP
9fn6erKuc0-FKbq4rjk4UpcAHIZf | Number of Tires/KSP (from idea to applying) | Fleet Management - app Infochiosc | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/29/2025 | 04/30/2025 |  | FALSE | FALSE | 05/22/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
N-Iy5dlrZkeSWcjUZbvdgZcAIZ9A | Improve CGMS DB - with (NOLOCK) - TIAS067A views | Scope | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Virlan, Claudia | 05/19/2025 | 05/15/2025 | 05/23/2025 | FALSE | FALSE | 05/21/2025 | Vulpes, Mihaela | 9/9 | ReportServer;NewERT_TEST;CuringCycleRecorder;MaintenanceDBSQL;NewERT;OzekiDB;ProductionData;PhoneListDB;BD_Timisoara | DB
RW9VpSE4vEeBnfR0Ryx4g5cABNnT | Improve CGMS DB - with (NOLOCK) - TIAS101A views | Scope | Completed | Medium | Vulpes, Mihaela | Virlan, Claudia | 05/19/2025 |  | 05/23/2025 | FALSE | FALSE | 05/21/2025 | Vulpes, Mihaela | 1/1 | ETL_DB | DB | Database: ETL_DB View: 1.[dbo].[Attendance] 2.[dbo].[Attendance_FleetM] 3.[dbo].[AttendanceTotalHours] 4.[dbo].[CGMS_Area_Workcenter] 5.[dbo].[CGMS_Lot_Operator] 6.[dbo].[CM_Complete_Pallet] 7.[dbo].[CM_Complete_Pallet_BKP] 8.[dbo].[Detailed_Production_V2] 9.[dbo].[LH_Rank_TB] 10.[dbo].[LH_Rank_TireBuilding] 11.[dbo].[LHPerformanceTB_area_records] 12.[dbo].[PBID_UnplannedMaintenance] 13.[dbo].[PBID_UnplannedMaintenance_new] 14.[dbo].[PBID_WO_Extrusion] 15.[dbo].[PBID_WODataExt] 16.[dbo].[PBID_WOExt_CGMS] 17.[dbo].[PBID_WOMachines] 18.[dbo].[ReworkTB] 19.[dbo].[vw_AttendanceHist] 20.[dbo].[vw_MissingMaterialsHour_Basis] 21.[dbo].[vw_MissingMaterialsHour_FirstPage] 22.[dbo].[vw_MMB_FirstPageTable] 23.[dbo].[vw_MMB_FirstPageTable_NovDec24] 24.[dbo].[vw_ProductionVolumes] Problematic views: 1.[dbo].[CM_Material_Consumption_Day] 3.[dbo].[PBID_MMS_Pallet_Dispo_Code] 4.[dbo].[PBID_MMS_Pallet_Dispo_Code_RW] 5.[dbo].[PBID_MMS_Pallet_Dispo_Code_RW_All] 6.[dbo].[PBID_MMS_Pallet_Dispo_Code_RW_All_ByShift] 7.[dbo].[PBID_PalletWeightTracker] 8.[dbo].[RW_Material_Consumption_Day] 9.[dbo].[RW_Material_Consumption_Day2] error: OLE DB provider "SQLNCLI11" for linked server "TITM09MMSMS01" returned message "Login timeout expired". OLE DB provider "SQLNCLI11" for linked server "TITM09MMSMS01" returned message "A network-related or instance-specific error has occurred while establishing a connection to SQL Server. Server is not found or not accessible. Check if instance name is correct and if SQL Server is configured to allow remote connections. For more information see SQL Server Books Online.". Msg -1, Level 16, State 1, Line 9 SQL Server Network Interfaces: Error Locating Server/Instance Specified [xFFFFFFFF]. Completion time: 2025-05-21T09:26:24.1570590+03:00 2.[dbo].[PBID_Mixing_Weighing] OLE DB provider "MSOLEDBSQL" for linked server "TITM09MMSMS01\TITMMMSSQL" returned message "Login timeout expired". OLE DB provider "MSOLEDBSQL" for linked server "TITM09MMSMS01\TITMMMSSQL" returned message "A network-related or instance-specific error has occurred while establishing a connection to SQL Server. Server is not found or not accessible. Check if instance name is correct and if SQL Server is configured to allow remote connections. For more information see SQL Server Books Online.". Msg -1, Level 16, State 1, Line 9 SQL Server Network Interfaces: Error Locating Server/Instance Specified [xFFFFFFFF]. Completion time: 2025-05-21T09:46:43.6779435+03:00
D992_HcmiEGaO-Bl8KAA-ZcAPh9U | FleetManager Infochiosc - monthly overview | Fleet Management - app Infochiosc | Completed | Medium | Donat, Cristian-Claudiu | Virlan, Claudia | 05/14/2025 |  |  | FALSE | FALSE | 05/15/2025 | Donat, Cristian-Claudiu |  |  | FleetM
WeCamgBYh0-kPODkC23YlpcAK6sn | ReworkTB | PowerBI stuff | Completed | Low | Vulpes, Mihaela | Vulpes, Mihaela | 05/08/2025 | 04/30/2025 | 04/30/2025 | FALSE | FALSE | 05/08/2025 | Vulpes, Mihaela | 4/4 | Import data;visual ;Adaugare slicere :operator , masina , date...;Structurare tabel | REWO | Raport simplu tabelar
T6-I2apKy0GnRdKVSQ2dFJcAEMpT | Unplanned Maintenance cleanup + navigare pagini | PowerBI stuff | Completed | Medium | Vulpes, Mihaela | Vulpes, Mihaela | 02/24/2025 |  | 05/07/2025 | FALSE | FALSE | 05/08/2025 | Vulpes, Mihaela | 0/3 | revizuire ;verificare navigare functionalitate;useless data | UnplannedM
oFO9s0tfNky8ANTYsXqlLZcADOK0 | Ticket - dataset Tracking Operatori dedicati IE | App REWO TB | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/05/2025 | 05/05/2025 | 05/06/2025 | FALSE | FALSE | 05/08/2025 | Virlan, Claudia | 7/8 | Add new spiltted column in the view;Split Description in substrings;Modify Stored Procedure sp_CGMS_Lot_Operator;Modify tbl_CGMS_Operator;Modify ETL : query, mapping. transform;Modify tbl_CGMS_Lot_Operator_stg;Modify view CGMS_Lot_Operator;Test PBI Refresh after modifications
xfV60kacNky5waCy729k7pcALuGt | CTOO - conectare PBIX to Mustang dopac/ctoo | Fleet Management - app Infochiosc | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/08/2025 | 05/08/2025 | 05/08/2025 | FALSE | FALSE | 05/08/2025 | Virlan, Claudia |  |  | CTOO
nPSsaFraWEqTJKNKORU3BZcAIM2p | ReworkTB Fix APP | Migrare CTOO - IE | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 05/06/2025 | 05/06/2025 | 05/06/2025 | FALSE | FALSE | 05/06/2025 | Donat, Cristian-Claudiu
_2NlqqLaIkSsguHwvhl21ZcAO2cQ | Infochiosk app for FLEETM | Migrare CTOO - IE | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/29/2025 |  | 05/15/2025 | FALSE | FALSE | 05/06/2025 | Donat, Cristian-Claudiu |  |  | FleetM
EnpFdePG9E20tU3y_iK585cAKjjE | CTOO - creare cerere acces Mustang - DOPAC | Fleet Management - app Infochiosc | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 05/05/2025 | 05/05/2025 | 05/05/2025 | FALSE | FALSE | 05/05/2025 | Virlan, Claudia |  |  | CTOO
LqAmCBPy8U2Ejh10mIpXxpcABouq | Ticket - Aducere date 24-28 aprilie in NCLotHistory PBI | Migrare CTOO - IE | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 04/29/2025 | 04/29/2025 | 04/29/2025 | FALSE | FALSE | 04/29/2025 | Virlan, Claudia
vBwQxiR4hUOaNI6hzfrkx5cAGLvg | (WarehouseTiretracking)TireDelete APP | Migrare CTOO - IE | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/16/2025 |  |  | FALSE | FALSE | 04/29/2025 | Donat, Cristian-Claudiu
yU3uVLvNaki_KJN1VZWTO5cAJdC8 | (WarehouseTiretracking)TireDelete History | TET - Travel Exp Tool | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/29/2025 |  |  | FALSE | FALSE | 04/29/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
lA4yR8HFsECJ69jLCpqhs5cAJvkN | (WarehouseTiretracking)TireSearch APP | TET - Travel Exp Tool | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/29/2025 |  |  | FALSE | FALSE | 04/29/2025 | Donat, Cristian-Claudiu |  |  | WareHouse
baWEbd2bdUK0ermhKwkK0pcAKuaK | LedPanels TB1 (Resizing) | App Production Planning | Completed | Medium |  | Donat, Cristian-Claudiu | 04/29/2025 |  |  | FALSE | FALSE | 04/29/2025 | Donat, Cristian-Claudiu
JY8JMYWBDEeRquJ1onsIUpcAC-wv | FleetManager PBI report - job FleetDrivers | Fleet Management - app Infochiosc | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 04/24/2025 | 04/25/2025 |  | FALSE | FALSE | 04/29/2025 | Virlan, Claudia |  |  | FleetM
eIk-NzN8wE-aTjHBhLS1sZcAJf3K | (WarehouseTiretracking)Presentation about TireTracking (Nr of Tires/KSP) | Scope | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 04/16/2025 | 04/21/2025 | 04/24/2025 | FALSE | FALSE | 04/29/2025 | Donat, Cristian-Claudiu
PNKwMf4CUk6pJPOfqpjqmZcAJlBj | FleetManager PBI report - evidentiere cazuri TotalShocks si ShockFreq | Migrare CTOO - IE | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 04/24/2025 | 04/24/2025 |  | FALSE | FALSE | 04/24/2025 | Virlan, Claudia |  |  | FleetM
RzdnOJ1IkEuR33doXumcKZcAIjVf | FleetManager PBI report - 24042025 | Migrare CTOO - IE | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 04/24/2025 | 04/24/2025 | 04/24/2025 | FALSE | FALSE | 04/24/2025 | Virlan, Claudia | 3/3 | ShiftDate - eliminare ora;afisare default ultima zi;stabilire ora Refresh 10 si 15 | FleetM
w3iW2NwflEKaYIF4BdUFIpcAJNXf | (WO DataCollection) Report testing and improvement(Moise Bujanca) | App REWO TB | Completed | Medium |  | Virlan, Claudia | 09/12/2024 | 11/18/2024 | 11/22/2024 | FALSE | FALSE | 04/24/2025 | Virlan, Claudia
oVbixtxj-kmvWXD1fjWQSJcAMIK3 | Lista de view-uri si Proceduri stocate TIAS101A | No Bucket | Completed | Medium | Vulpes, Mihaela | Virlan, Claudia | 04/03/2025 |  | 04/11/2025 | FALSE | FALSE | 04/04/2025 | Vulpes, Mihaela |  |  | DB
nzagqb-XCkuz9SyT_HvrY5cABkZF | Work off Data Collection | PowerBI stuff | Completed | Important | Vulpes, Mihaela | Vulpes, Mihaela | 02/12/2025 | 02/20/2025 | 03/10/2025 | FALSE | FALSE | 03/11/2025 | Vulpes, Mihaela | 4/4 | WO% generat pe compundul selectat ;nr de buc generate pe articol pentru compundul selectat;validare;total productie pe compoundul respectiv | Blocked | - La selectia unui tip de compound toate celelalte campuri sa se schimbe corespunzator - Se calculeaza procentul de generare pe tip de material (suma articolelor produse cu materialul respectiv vs suma WO produs din art ) - ( total tread produs pe compundul respectiv / total wo generat pe tread respectiv)
vljA0rw0h0e__zhQ3UIAJ5cAKtzg | Raport raw data QM - analiza preliminara | No Bucket | Completed | Important | Virlan, Claudia | Virlan, Claudia | 11/28/2024 | 11/29/2024 | 12/04/2024 | FALSE | FALSE | 03/04/2025 | Virlan, Claudia |  |  |  | Ca punct de plecare este crearea raportului folosind ca template ce este acum disponibil in Grading: [QMB00470 - List Analysis BC Basic Data_Excel - SQL Server 2019 Reporting Services](http://titm15c02db02/Reports/report/Reporting%20Grading/QMB00470%20-%20List%20Analysis%20BC%20Basic%20Data_Excel) la care se adauga urmatoarele: - Postul de lucru (Grading 1, 2, 3 in functie PC ID / IP) Culoarea schimbului (e nevoie de table cu shift rotation)
vY5uA1NGq0mye3aCF2ykZ5cAB0JT | Missing Material UPDATE | PowerBI stuff | Completed | Important | Vulpes, Mihaela | Vulpes, Mihaela | 02/24/2025 | 02/20/2025 | 03/20/2025 | FALSE | FALSE | 03/03/2025 | Vulpes, Mihaela | 3/3 | add Nov & Dec ;sync slicer MM & OH & Total;fix titles Extrusion & Cutting | UnplannedM | "ar fi util ca daca bifez spre exemplu "doar missing material" sa ramana bifat si daca trec de la o fereastra la alta. Acum, se reseteaza de cate ori trec. In plus, la Total Cutting apare ca si titlu Calandru, ceea ce sigur este gresit. Ar fi util daca ai putea adauga si Noiembrie si Decembrie."
wcDqMDsRtkmKAPy2772z-pcAKgrP | Volume Benchmark Update | PowerBI stuff | Completed | Important | Vulpes, Mihaela | Vulpes, Mihaela | 02/12/2025 | 02/04/2025 | 02/20/2025 | FALSE | FALSE | 02/24/2025 | Vulpes, Mihaela | 6/6 | Apex/ Bead;Curing ;Cutting ;TB cu TB by GROUP ;validare;Extrusion ( exceptie combi sidewall monthly overall & sidewall monthly by machines EXDX1) | High | O scala predefinita fixa pentru fiecare proces (Monthly Overall + Monthly by Machines ) sub 5000 -> 500 5000 - 20000 -> 1000 or 2000 peste 50000 -> 10000
Lvf_ysC7vUO0trUjINA9aJcAHXkG | (WO DataCollection) Admin Interface Testing (Anita A) | App REWO TB | Completed | Medium |  | Donat, Cristian-Claudiu | 09/11/2024 | 10/28/2024 | 11/01/2024 | FALSE | FALSE | 02/13/2025 | Virlan, Claudia
bP-6gr8gPEGumG-Mo1QlAJcAC5Xq | (WO DataCollection) Go Live on one pilot TPX machine | TET - Travel Exp Tool | Completed | Medium |  | Virlan, Claudia | 09/12/2024 | 10/24/2024 | 10/31/2024 | FALSE | FALSE | 02/13/2025 | Virlan, Claudia
LAPVO80lG0-wqkjA4JkoJZcAOfVt | De creat job pentru actualizare WODataExt (tias009/WODataColl) | Migrare CTOO - IE | Completed | Medium |  | Virlan, Claudia | 09/25/2024 |  | 10/18/2024 | FALSE | FALSE | 02/13/2025 | Virlan, Claudia |  |  |  | Donat, Cristian-Claudiu in Chat with Claudia-Ioana at September 24 2024, 9:37 AM: De creat job pentru actualizare WODataExt (tias009/WODataColl) https://teams.microsoft.com/l/message/19:079a04f8-ab41-47ba-97a2-814ae4a99eac_8eb099d5-26a6-4e73-81d5-3395fd89615f@unq.gbl.spaces/1727159852175?context=%7B%22contextType%22:%22chat%22%7D
EFFX1dJAskWQ4Z02ClfHJJcAALZO | Verificare mod de calcul Average pt VolumeBenchmark | No Bucket | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 01/13/2025 |  |  | FALSE | FALSE | 02/13/2025 | Virlan, Claudia
a1Inf-OaCEaFw1gYEwP905cAO_Wa | (WO DataCollection) Deliver report | TET - Travel Exp Tool | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 09/12/2024 | 11/25/2024 | 11/29/2024 | FALSE | FALSE | 02/13/2025 | Virlan, Claudia
2m7day6bhEisyj_PQ-pR65cAP5Fq | MissingMaterialsHourlyBenchmark_Test | PowerBI stuff | Completed | Urgent | Vulpes, Mihaela | Vulpes, Mihaela | 02/12/2025 | 01/09/2025 | 02/13/2025 | FALSE | FALSE | 02/12/2025 | Vulpes, Mihaela | 4/4 | revizuire finala ;Monthly Overall & Daily Overall ;slicer with: Missing Material , On Hold Material , Total (MM & OH);get rid of useless bookmarks & pages | High | TB Missing Material & On Hold Material : Extrusion: - no/hold tread - no/on hold sidewall - no/on hold innerliner - Total (tread + sidewall + innerliner ) Cutting : - no/on hold ply - no/on hold cap ply - no/ on hold bead reinforcement - no/ on hold breaker - Total Apex : - no/ on hold beads, bead assembly TB : Total Extrusion + Cutting + Apex
vbtPYfPSzEGX8f4OKHfrPZcAIwCC | Update Cutting : Add Cap Strip 1 & 2 ( CXCS1 & CXCS2) | PowerBI stuff | Completed | Medium | Vulpes, Mihaela | Vulpes, Mihaela | 02/12/2025 | 02/10/2025 | 02/14/2025 | FALSE | FALSE | 02/12/2025 | Vulpes, Mihaela | 3/3 | Cap Strip Daily by Machines ;Monthly Overall ( add Cap Strip 2 -> filter for clustered column chart ) ;Cap Strip Monthly by Machines
elSl1RaOqkWdre42UqwtpZcAGLQh | (WO DataCollection) Report design (Moise B + Claudia V) | App Production Planning | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 09/12/2024 | 11/04/2024 | 11/08/2024 | FALSE | FALSE | 11/28/2024 | Virlan, Claudia
bl_NOSqzyECopEP06-A-45cAFctd | (WO DataCollection) Create raport based on data collected | Migrare CTOO - IE | Completed | Medium | Vulpes, Mihaela;Virlan, Claudia | Virlan, Claudia | 09/12/2024 | 11/11/2024 | 11/15/2024 | FALSE | FALSE | 11/12/2024 | Virlan, Claudia
H8OvHOg-R0GDkZ_y8crSdJcAMzVh | (WO DataCollection) User Interface Testing (Florin Todica) | App REWO TB | Completed | Medium |  | Donat, Cristian-Claudiu | 09/11/2024 | 10/14/2024 | 10/18/2024 | FALSE | FALSE | 11/01/2024 | Donat, Cristian-Claudiu
KGhUu30js0eS9SL6tFyNTpcAAK4F | (WO DataCollection) Create database structure | Migrare CTOO - IE | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 09/12/2024 | 09/03/2024 | 09/06/2024 | FALSE | FALSE | 09/12/2024 | Virlan, Claudia
PP1dU09wLU24L-Z-Sj7OMJcABfXf | (WO DataCollection) Design Visual Interface | App Production Planning | Completed | Medium | Donat, Cristian-Claudiu | Donat, Cristian-Claudiu | 09/11/2024 | 09/02/2024 | 09/09/2024 | FALSE | FALSE | 09/11/2024 | Donat, Cristian-Claudiu
R_XRmh9RlkikPnLSommfoJcACwSS | (WO DataCollection) Design Database Structure | App Production Planning | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 09/11/2024 | 09/02/2024 | 09/03/2024 | FALSE | FALSE | 09/11/2024 | Virlan, Claudia
Os-XFYHnk0CVTtiGGE-L65cAMwhx | (WO DataCollection) Analyze Data Sources | Fleet Management - app Infochiosc | Completed | Medium | Virlan, Claudia | Virlan, Claudia | 09/11/2024 | 09/02/2024 | 09/03/2024 | FALSE | FALSE | 09/11/2024 | Virlan, Claudia